MELTON LOCAL PLAN – TIMELINE: JULY 2013

| KEY PROCESS | PURPOSE | TIMELINE |
| --- | --- | --- |
| 1. Engagement Process | Produce communication strategy and Statement of Community Involvement. Create reference groups and undertake initial training. Regulation 18 Consultation on principles for growth and development of the Borough of Melton and Melton Mowbray. | June 2013 – January 2014 |
| 2. Strategic Decisions | Determine the housing requirements for the Borough; examine alternative urban/rural split; and, review settlement hierarchy including rural centre/village distribution. | May – December 2013 |
| 3. Housing Options | Identify strategic housing sites and refine to three or four options. | August 2013 – January 2014 |
| 4. Traffic Modelling | Produce brief for LLITM and run model to assess strategic options and possible mitigation measures. Review outputs (possible re-run of model and reassessment). | August 2013 – March 2014 |
| 5. Options Appraisal | Undertake review of available options including intensive community involvement with 6 week formal consultation period. | Summer 2014 |
| 6. Preferred Option | Agree Preferred Option following assessment of consultation responses. | Autumn 2014 |
| 7. Produce Publication Local Plan | Draft Chapters; define Site Allocations; produce Policies Map/s. Consult reference groups and report Publication local Plan to Full Council. | Autumn 2014 – Summer 2015 |
| 8. Consultation on Publication Local Plan | Consult on Publication Local Plan for statutory 6 weeks. Analyse responses, negotiate possible changes and produce Schedule of Changes. | Autumn - Winter 2015 |
| 9. Submission and Examination | Report Submission Local Plan to Full Council and submit. Prepare topic papers and respond to Inspector’s questions. Hearing and Inspector’s report. | Spring - Winter 2016 |
| 10. Adoption | Report to Full Council and Adopt | Spring 2017 |